## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
Sprint 1 | Sprint 1 | US-01 | Candidate registration and login | Must | Authentication | CHIMATA RAGHURAM | 3- Completed
Sprint 1 | Sprint 1 | US-02 | Candidate profile management | Should | US-01 | NARLA SAHITHYA REDDY | 3- Completed
Sprint 1 | Sprint 1 | US-03 | Admin authentication and access control | Must | Authentication | NARLA SAHITHYA REDDY | 3- Completed
Sprint 1 | Sprint 1 | US-04 | Examination setup and candidate access | Must | US-03 | SIREESHA JONNADA | 3- Completed
Sprint 1 | Sprint 1 | US-05 | Candidate dashboard and examination status | Must | US-01, US-04 | CHIMATA RAGHURAM | 3- Completed
Sprint 2 | Sprint 2 | US-06 | System readiness diagnostics | Must | US-04 | THOTA SATHWIKA | 3- Completed
Sprint 2 | Sprint 2 | US-07 | Camera-based candidate monitoring | Must | US-06 | CHIMATA RAGHURAM | 3- Completed
Sprint 2 | Sprint 2 | US-08 | Face-not-detected event logging | Must | US-07 | CHIMATA RAGHURAM | 3- Completed
Sprint 2 | Sprint 2 | US-09 | Multiple-face detection | Must | US-07 | SIREESHA JONNADA | 3- Completed
Sprint 2 | Sprint 2 | US-10 | Browser focus and tab monitoring | Must | US-06 | THOTA SATHWIKA | 3- Completed
Sprint 3 | Sprint 3 | US-11 | EventLog and examination session tracking | Must | US-07, US-10 | SIREESHA JONNADA | 3- Completed
Sprint 3 | Sprint 3 | US-12 | Integrity score calculation | Must | US-11 | CHIMATA RAGHURAM | 3- Completed
Sprint 3 | Sprint 3 | US-13 | Candidate activity timeline | Should | US-11 | NARLA SAHITHYA REDDY | 3- Completed
Sprint 3 | Sprint 3 | US-14 | Monitoring statistics and event summary | Should | US-11 | THOTA SATHWIKA | 3- Completed
Sprint 3 | Sprint 3 | US-15 | Detailed examination integrity report | Must | US-12 | CHIMATA RAGHURAM | 3- Completed
Sprint 4 | Sprint 4 | US-16 | Admin monitoring dashboard | Must | US-03, US-11 | NARLA SAHITHYA REDDY | 3- Completed
Sprint 4 | Sprint 4 | US-17 | Live candidate monitoring view | Must | US-11 | SIREESHA JONNADA | 3- Completed
Sprint 4 | Sprint 4 | US-18 | Suspicious alerts and event logs | Must | US-11 | SIREESHA JONNADA | 3- Completed
Sprint 4 | Sprint 4 | US-19 | Report export and download | Should | US-15 | THOTA SATHWIKA | 3- Completed
Sprint 5 | Sprint 5 | US-20 | Candidate AI assistant | Could | US-01, US-11 | CHIMATA RAGHURAM | 3- Completed
Sprint 5 | Sprint 5 | US-21 | Admin AI assistant | Could | US-03, US-11 | CHIMATA RAGHURAM | 3- Completed
Sprint 5 | Sprint 5 | US-22 | Personalized candidate score and event queries | Could | US-12 | CHIMATA RAGHURAM | 3- Completed
Sprint 5 | Sprint 5 | US-23 | Admin score, risk and candidate-list queries | Could | US-21 | NARLA SAHITHYA REDDY | 3- Completed
Sprint 5 | Sprint 5 | US-24 | Final UI, integration and responsive validation | Should | US-05, US-16 | THOTA SATHWIKA | 3- Completed
Note on F1: ====== ID#AAABcShYZQo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
SPRINT 1 BACKLOG
US-01 | T-01 | Implement candidate registration and login | 2026-08-01 | 2026-08-02 | CHIMATA RAGHURAM | Coding | 3- Completed | 4 | Day 1: 4
US-03 | T-02 | Implement admin authentication | 2026-08-01 | 2026-08-02 | NARLA SAHITHYA REDDY | Coding | 3- Completed | 4 | Day 1: 4
US-02 | T-03 | Build candidate profile page | 2026-08-02 | 2026-08-04 | NARLA SAHITHYA REDDY | UI | 3- Completed | 5 | Day 1: 5
US-04 | T-04 | Connect examination and session data | 2026-08-03 | 2026-08-05 | SIREESHA JONNADA | Backend | 3- Completed | 6 | Day 1: 6
US-05 | T-05 | Build candidate dashboard | 2026-08-04 | 2026-08-07 | CHIMATA RAGHURAM | UI | 3- Completed | 8 | Day 1: 8
SPRINT 2 BACKLOG
US-06 | T-06 | Implement system readiness diagnostics | 2026-08-08 | 2026-08-09 | THOTA SATHWIKA | Development | 3- Completed | 6 | Day 1: 6
US-07 | T-07 | Implement camera monitoring flow | 2026-08-08 | 2026-08-11 | CHIMATA RAGHURAM | Coding | 3- Completed | 10 | Day 1: 8; Day 2: 2
US-08 | T-08 | Record face-not-detected events | 2026-08-10 | 2026-08-12 | CHIMATA RAGHURAM | Backend | 3- Completed | 6 | Day 1: 6
US-09 | T-09 | Implement multiple-face detection | 2026-08-10 | 2026-08-13 | SIREESHA JONNADA | Coding | 3- Completed | 8 | Day 1: 8
US-10 | T-10 | Implement browser focus monitoring | 2026-08-11 | 2026-08-14 | THOTA SATHWIKA | Coding | 3- Completed | 8 | Day 1: 8
SPRINT 3 BACKLOG
US-11 | T-11 | Implement EventLog and session queries | 2026-08-15 | 2026-08-17 | SIREESHA JONNADA | Backend | 3- Completed | 8 | Day 1: 8
US-12 | T-12 | Implement integrity score rules | 2026-08-15 | 2026-08-18 | CHIMATA RAGHURAM | Analytics | 3- Completed | 7 | Day 1: 7
US-13 | T-13 | Build activity timeline | 2026-08-17 | 2026-08-19 | NARLA SAHITHYA REDDY | UI | 3- Completed | 6 | Day 1: 6
US-14 | T-14 | Build monitoring statistics | 2026-08-18 | 2026-08-20 | THOTA SATHWIKA | Analytics/UI | 3- Completed | 6 | Day 1: 6
US-15 | T-15 | Build detailed integrity report | 2026-08-19 | 2026-08-21 | CHIMATA RAGHURAM | Reporting | 3- Completed | 8 | Day 1: 8
SPRINT 4 BACKLOG
US-16 | T-16 | Build admin monitoring dashboard | 2026-08-22 | 2026-08-23 | NARLA SAHITHYA REDDY | UI | 3- Completed | 7 | Day 1: 7
US-17 | T-17 | Build live monitoring page | 2026-08-22 | 2026-08-24 | SIREESHA JONNADA | UI | 3- Completed | 7 | Day 1: 7
US-18 | T-18 | Build suspicious alerts and event logs | 2026-08-23 | 2026-08-25 | SIREESHA JONNADA | UI/Backend | 3- Completed | 7 | Day 1: 7
US-19 | T-19 | Implement report export/download | 2026-08-24 | 2026-08-26 | THOTA SATHWIKA | Reporting | 3- Completed | 6 | Day 1: 6
SPRINT 5 BACKLOG
US-20 | T-20 | Integrate candidate AI assistant | 2026-08-27 | 2026-08-28 | CHIMATA RAGHURAM | AI Integration | 3- Completed | 8 | Day 1: 8
US-21 | T-21 | Integrate admin AI assistant | 2026-08-27 | 2026-08-29 | CHIMATA RAGHURAM | AI Integration | 3- Completed | 8 | Day 1: 8
US-22 | T-22 | Add personalized candidate queries | 2026-08-28 | 2026-08-29 | CHIMATA RAGHURAM | AI/Backend | 3- Completed | 5 | Day 1: 5
US-23 | T-23 | Add admin score and candidate-list queries | 2026-08-28 | 2026-08-29 | NARLA SAHITHYA REDDY | AI/Backend | 3- Completed | 6 | Day 1: 6
US-24 | T-24 | Perform final UI and responsive validation | 2026-08-27 | 2026-08-29 | THOTA SATHWIKA | UI/QA | 3- Completed | 6 | Day 1: 6
Note on D2: ====== ID#AAABcShYZRI Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on E2: ====== ID#AAABcShYZRU Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on I3: ====== ID#AAABcShYZQ4 Sumeet Kumar Barua08 (2025-01-27 09:44:41) This is the total task estimated in hours for all the user stories
Note on J3: ====== ID#AAABcShYZRc Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 1 work
Note on K3: ====== ID#AAABcShYZRg Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 2 work
Note on L3: ====== ID#AAABcShYZQs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 3 work
Note on M3: ====== ID#AAABcShYZRo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 4 work
Note on N3: ====== ID#AAABcShYZQw Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 5 work
Note on O3: ====== ID#AAABcShYZRk Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 6 work
Note on P3: ====== ID#AAABcShYZRY Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 7 work
Note on Q3: ====== ID#AAABcShYZRA Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 8 work
Note on R3: ====== ID#AAABcShYZRs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 9 work
Note on S3: ====== ID#AAABcShYZRM Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 10 work
Note on T3: ====== ID#AAABcShYZRE Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 11 work
Note on U3: ====== ID#AAABcShYZQ8 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 12 work
Note on V3: ====== ID#AAABcShYZQ0 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 13 work
Note on W3: ====== ID#AAABcShYZRQ Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint 1 | Day 1 | Project scope and ownership needed alignment. | Reviewed requirements and divided candidate, admin, backend and testing responsibilities.
Sprint 1 | Day 4 | Candidate and admin flows needed clearer separation. | Mapped user journeys and aligned navigation.
Sprint 2 | Day 2 | Camera permissions required browser-specific checks. | Tested camera access and readiness flow.
Sprint 2 | Day 5 | Monitoring events needed consistent logging. | Validated face and browser-focus event handling.
Sprint 3 | Day 2 | Integrity score needed session-specific event data. | Connected score calculation to current-session events.
Sprint 3 | Day 5 | Report needed clearer event summary. | Refined report sections and event presentation.
Sprint 4 | Day 2 | Admin dashboard contained too much information. | Separated admin functions into focused views.
Sprint 4 | Day 5 | UI spacing needed consistency across pages. | Standardized cards, navigation and spacing.
Sprint 5 | Day 2 | AI responses needed application-specific context. | Connected assistant queries to available project data.
Sprint 5 | Day 4 | Final repository needed submission review. | Checked documentation, source structure and required files.

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | 1 | 2026-08-01 | 2026-08-07 | CHIMATA RAGHURAM | Document UI/API decisions earlier. | Changing layouts without integration checks. | Frequent team coordination. | Added a checklist before UI changes.
2 | 1 | 2026-08-01 | 2026-08-07 | NARLA SAHITHYA REDDY | Review admin flow before implementation. | Late UI feedback. | Clear module ownership. | Reviewed authentication and profile flow together.
3 | 2 | 2026-08-08 | 2026-08-14 | SIREESHA JONNADA | Validate monitoring events earlier. | Assuming browser behavior is identical. | Backend event review. | Added repeatable monitoring checks.
4 | 2 | 2026-08-08 | 2026-08-14 | THOTA SATHWIKA | Run readiness and statistics checks earlier. | Waiting until the end for validation. | Incremental testing. | Added readiness/statistics checks to sprint testing.
5 | 3 | 2026-08-15 | 2026-08-21 | CHIMATA RAGHURAM | Validate reports against EventLog earlier. | Duplicating data retrieval logic. | Cross-module integration reviews. | Centralized session/event usage for reports.
6 | 4 | 2026-08-22 | 2026-08-26 | NARLA SAHITHYA REDDY | Review dashboard navigation earlier. | Keeping too many functions on one page. | Focused page structure. | Separated admin dashboard functions.
7 | 5 | 2026-08-27 | 2026-08-29 | SIREESHA JONNADA | Perform repository checks before the final day. | Leaving cleanup until submission time. | Team verification. | Reviewed source organization and documentation.