## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
DEF-01 | CHIMATA RAGHURAM | 2026-08-06 | Candidate dashboard needed clearer information hierarchy. | Sprint 1 | CHIMATA RAGHURAM | User Interface | Improved dashboard layout and spacing. | 2026-08-07 | Closed | Reviewed after UI update.
DEF-02 | NARLA SAHITHYA REDDY | 2026-08-12 | Admin flow needed clearer separation between authentication and dashboard. | Sprint 2 | NARLA SAHITHYA REDDY | User Interface | Refined admin navigation and flow. | 2026-08-13 | Closed | Admin flow reviewed.
DEF-03 | SIREESHA JONNADA | 2026-08-14 | Multiple-face events needed clearer activity presentation. | Sprint 2 | SIREESHA JONNADA | User Interface | Improved event display and remarks. | 2026-08-14 | Closed | Activity presentation reviewed.
DEF-04 | CHIMATA RAGHURAM | 2026-08-20 | Integrity report needed clearer event summary and timeline. | Sprint 3 | CHIMATA RAGHURAM | User Interface | Refined report sections and event summary. | 2026-08-21 | Closed | Report reviewed.
DEF-05 | THOTA SATHWIKA | 2026-08-25 | Statistics and report views needed consistent spacing. | Sprint 4 | THOTA SATHWIKA | User Interface | Standardized cards and spacing. | 2026-08-26 | Closed | Statistics and report pages reviewed.
DEF-06 | NARLA SAHITHYA REDDY | 2026-08-26 | Admin dashboard contained too much information on one page. | Sprint 4 | NARLA SAHITHYA REDDY | User Interface | Separated admin features into focused navigation pages. | 2026-08-26 | Closed | Navigation reviewed.
DEF-07 | CHIMATA RAGHURAM | 2026-08-28 | AI assistant responses needed more project-specific context. | Sprint 5 | CHIMATA RAGHURAM | Logical | Connected assistant queries to available application data. | 2026-08-29 | Closed | Candidate/admin query scenarios reviewed.
DEF-08 | THOTA SATHWIKA | 2026-08-29 | README project tree and command formatting rendered incorrectly. | Sprint 5 | THOTA SATHWIKA | Standards | Corrected Markdown formatting and run instructions. | 2026-08-29 | Closed | README rendering reviewed.

## Sheet2
Logical
User Interface
Maintainability
Standards
Others